## Read Me
SafePath Berlin – UAT Test Scenarios
User Acceptance Testing pack focused on UX, UI and user convenience
About this workbook
This workbook contains User Acceptance Test (UAT) scenarios for the SafePath Berlin web app (https://safepath.duckdns.org/home), written from an end user's point of view. The 'UAT Test Cases' sheet covers the Home / route search screen, route details, login, registration, incident reporting, profile management, the AI chat assistant, and general cross-device usability. The 'Admin UAT Test Cases' sheet (same layout) covers the Admin Dashboard: role-based access, Overview, Search Logs, Incident Logs, User Management, and Login Logs.
How to use
1. Go to the 'UAT Test Cases' sheet.
2. For each Test ID, follow the Test Steps against the Preconditions and Test Data given.
3. Record the Test Device / Browser used for that run.
4. Fill in Actual Result with what you observed.
5. Set Status using the dropdown: Pass, Fail, Blocked, or Not Executed.
6. Add any Remarks (bugs, suggestions, screenshots reference, ticket number, etc.).
7. Use the Summary sheet to track overall pass/fail progress.
Column guide
• Test ID: Unique ID per scenario, prefixed by module (e.g. HOME-01, LOGIN-02).
• Module: App area / page being tested.
• Test Scenario: Short title of what is being verified.
• Test Steps: Numbered steps to reproduce.
• Preconditions: State required before starting (e.g. logged in, on mobile).
• Test Data: Example input values to use.
• Expected Result: What should happen if the feature works correctly.
• Test Device / Browser: Device + browser combination used for this run.
• Actual Result: What actually happened – fill in during testing.
• Status: Pass / Fail / Blocked / Not Executed.
• Priority: How critical this scenario is (High / Medium / Low).
• Tester: Name of the person who executed the test.
• Test Date: Date the test was executed.
• Remarks: Bugs found, screenshots, follow-up notes.
Note: this workbook currently shows a completed test run (all scenarios marked Pass, dated 2026-08-15). Remarks include a few Pass items with 'nice to have' or convenience notes spotted during testing — these did not fail the test, they are just suggestions for a future iteration. To start a fresh run, clear the Actual Result, Status, Tester, Test Date, and Remarks columns on the Test Cases sheets.

## UAT Test Cases
Test ID | Module | Test Scenario | Test Steps | Preconditions | Test Data | Expected Result | Test Device / Browser | Actual Result | Status | Priority | Tester | Test Date | Remarks
HOME-01 | Home / Route Search | Search for a safe route without logging in | 1. Open https://safepath.duckdns.org/home without logging in. 2. Enter a start location. 3. Enter a destination. 4. Click 'Search Safe Route'. | App is loaded, user is not logged in | Start: Alexanderplatz Destination: Brandenburg Gate | User can search and view route options without needing to log in first. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-02 | Home / Route Search | Location autocomplete suggestions appear while typing | 1. Click into the 'Start Location' field. 2. Type a partial place name. 3. Observe the suggestion dropdown. 4. Select a suggestion. | On Home page | Type: 'Alexander' | A dropdown of matching place suggestions appears within ~1-2 seconds and clicking one fills the field correctly. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: bold or highlight the matching text inside each suggestion so it is faster to scan.
HOME-03 | Home / Route Search | Switch between Walking and Driving travel mode | 1. On Home page, locate the Walking/Driving toggle. 2. Tap 'Driving'. 3. Enter start and destination. 4. Tap 'Search Safe Route'. 5. Repeat with 'Walking' selected. | On Home page | Any valid start/destination pair | Selected mode is visually highlighted, and returned routes/duration change appropriately to match the chosen mode. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience idea: remember the traveller's last-used mode (walking/driving) for their next visit.
HOME-04 | Home / Route Search | Clear button resets the search form | 1. Fill in Start Location and Destination fields. 2. Click the 'Clear' button. | Fields have values entered | Any values | Both fields (and any shown results/pins) are cleared back to empty state. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-05 | Home / Route Search | Search with an invalid or unrecognisable location | 1. Enter a nonsense value (e.g. 'zzxxqq123') into Destination. 2. Click 'Search Safe Route'. | On Home page | Destination: 'zzxxqq123' | App shows a clear, friendly error/no-results message instead of freezing or showing a blank screen. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-06 | Home / Route Search | Search with empty Start or Destination field | 1. Leave 'Start Location' empty. 2. Enter a valid Destination. 3. Click 'Search Safe Route'. | On Home page | Destination: 'Museum Island' | App prevents submission or shows a validation message asking for the missing field, rather than erroring silently. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-07 | Home / Route Search | Multiple route options are displayed with names | 1. Perform a valid route search. 2. Review the list of returned route cards. | Search returns at least one result | Start: Hauptbahnhof, Destination: Alexanderplatz | At least one route option is shown, each with a readable name/label and a 'View Details' action. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: show a small safety-score badge directly on each route card, not only after opening details.
HOME-08 | Home / Route Search | Map updates to reflect the searched route | 1. Perform a valid route search. 2. Observe the map panel. | Search returns at least one result | Start: Hauptbahnhof, Destination: Alexanderplatz | Map re-centres/zooms to show the route path and start/end markers clearly, without needing manual zoom. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-09 | Home / Route Search | 'View Details' on a route prompts login for guest user | 1. As a guest (not logged in), search for a route. 2. Click 'View Details' on a route card. | User is NOT logged in | Any completed search | A 'Login required' dialog appears explaining detailed route safety is for registered users, with Login/Cancel options. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
HOME-10 | Home / Route Search | 'View Details' opens Route Details page for logged-in user | 1. Log in. 2. Search for a route. 3. Click 'View Details' on a route card. | User is logged in | Any completed search | User is taken directly to the Route Details page for that route, no login prompt appears. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ROUTE-01 | Route Details | Route details show distance, duration, and route type | 1. Log in and open a route's details page. 2. Review the summary list. | Logged in, viewing a Route Details page | Any selected route | Distance covered, estimated duration, and route type are all shown with correct, readable values. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ROUTE-02 | Route Details | Journey (start → destination) is clearly labelled | 1. Open a Route Details page. 2. Check the 'Journey' field. | Logged in, viewing a Route Details page | Any selected route | Journey field clearly shows start and destination in an easy-to-read format. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ROUTE-03 | Route Details | 'Back to Search' returns user to Home with results intact | 1. On Route Details page, click 'Back to Search'. | Arrived at Route Details from a Home search | N/A | User is returned to the Home page; ideally previous search/results are still visible rather than reset. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
LOGIN-01 | Login | Successful login with valid email and password | 1. Go to Login page. 2. Enter valid registered email and password. 3. Click 'Login'. | An account already exists | Valid test account credentials | User is logged in and redirected to the Home page; nav shows logged-in state (e.g. profile access). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
LOGIN-02 | Login | Login fails gracefully with wrong password | 1. Go to Login page. 2. Enter a valid email with an incorrect password. 3. Click 'Login'. | An account already exists | Valid email, wrong password | A clear error message is shown; user is not logged in and password field is easy to correct. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
LOGIN-03 | Login | Social/provider login button works | 1. Go to Login page. 2. Click one of the listed identity provider buttons. | On Login page | N/A | User is redirected to the provider's auth flow and, on success, returns logged in to SafePath. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: consider adding an Apple sign-in option alongside the existing provider for iOS users.
LOGIN-04 | Login | 'Click to register' link navigates to Register page | 1. On Login page, click the register link/prompt. | On Login page | N/A | User is taken to the Register page without errors. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
LOGIN-05 | Login | Password field masks input | 1. On Login page, click into the password field. 2. Type a password. | On Login page | Any string | Characters are shown as dots/asterisks, not plain text, and there's no obvious way to accidentally reveal it. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
REG-01 | Register | Successful registration with valid details | 1. Go to Register page. 2. Enter Name, Email, and Password. 3. Click 'Create Account'. | Email is not already registered | Name: Test User, Email: newuser@test.com, Password: Test1234! | Account is created, user receives confirmation/is logged in, and is redirected appropriately. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: a password-strength meter would help users pick a stronger password on the first try.
REG-02 | Register | Registration blocks duplicate email | 1. Go to Register page. 2. Enter an email that is already registered. 3. Click 'Create Account'. | Test account with this email already exists | Existing account email | A clear error explains the email is already in use, with no duplicate account created. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
REG-03 | Register | Registration validates email format | 1. Go to Register page. 2. Enter an invalid email (e.g. 'notanemail'). 3. Attempt to submit. | On Register page | Email: 'notanemail' | Form shows inline validation and blocks submission until a valid email format is entered. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
REG-04 | Register | 'Login here' link on Register page works | 1. On Register page, click 'Login here'. | On Register page | N/A | User is taken to the Login page. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
INC-01 | Incident Report | Submit a valid incident report | 1. Go to Incident Report page. 2. Fill Reporter Name (optional), Incident Type, Location, Date, Time, and Details. 3. Click 'Submit Report'. | On Incident Report page | Type: Poor lighting; Location: Alexanderplatz; Date: today; Time: 20:30; Details: 'Street light not working near station exit' | A success message/alert is shown, and the new report appears in the reports list below. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
INC-02 | Incident Report | Required fields are enforced (Incident Type, Date, Time, Details) | 1. Go to Incident Report page. 2. Leave 'Incident Type' empty. 3. Fill remaining fields and click 'Submit Report'. | On Incident Report page | Details filled, Incident Type left blank | Submission is blocked with a clear indication of which required field(s) are missing. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
INC-03 | Incident Report | Report can be submitted anonymously | 1. Go to Incident Report page. 2. Leave 'Reporter Name' blank. 3. Fill required fields and submit. | On Incident Report page | Reporter Name left blank | Report submits successfully without requiring a name; listed as anonymous. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
INC-04 | Incident Report | Location autocomplete works on Incident Report form | 1. Click into 'Location' field. 2. Type a partial address. 3. Select a suggestion from the dropdown. | On Incident Report page | Type: 'Potsda' | Matching suggestions appear and selecting one correctly fills the Location field. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
INC-05 | Incident Report | Time picker works correctly | 1. Click into the 'Time' field. 2. Use the time picker widget to select a time. | On Incident Report page | Select any time, e.g. 21:15 | Time picker opens as an overlay, selected time populates the field accurately, and picker closes cleanly. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: default the date field to today so reporters only need to set the time.
INC-06 | Incident Report | Submitted reports list paginates correctly | 1. Go to Incident Report page. 2. Scroll to the reports list. 3. If more than one page exists, click through pagination controls. | More reports exist than fit on one page | N/A | Pagination correctly navigates between pages without errors or duplicate/missing entries. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: add a 'jump to page' input for long report lists instead of only next/previous.
INC-07 | Incident Report | Empty state message shown when no reports exist | 1. View Incident Report page on an account/context with zero submitted reports. | No reports exist yet | N/A | An informative 'No reports submitted yet' style message is shown instead of a blank list. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
PROFILE-01 | Profile | Profile displays correct account details | 1. Log in. 2. Go to Profile page. 3. Review First Name, Last Name, Email, Login Provider, Member Since. | Logged in | Logged-in test account | All displayed fields match the account's actual registered details, with no placeholder or blank values. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: show 'Member since' as a relative time too (e.g. '3 months ago').
PROFILE-02 | Profile | Delete account requires typing DELETE to confirm | 1. On Profile page, click 'Delete my account'. 2. In the confirmation dialog, leave the confirmation field empty or type something other than DELETE. | Logged in, on Profile page | Type: 'delete' (lowercase) or leave blank | The 'Delete' confirm button stays disabled until the exact word DELETE is typed, preventing accidental deletion. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
PROFILE-03 | Profile | Cancel on delete-account dialog aborts safely | 1. Click 'Delete my account'. 2. In the dialog, click 'Cancel'. | Logged in, on Profile page | N/A | Dialog closes, account is untouched, user remains logged in on Profile page. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
CHAT-01 | AI Chat Assistant | Chat widget loads on Home page | 1. Open Home page. 2. Locate the chat assistant widget. | On Home page, page fully loaded | N/A | Chat widget/icon loads within a reasonable time and does not block or overlap other key controls (search form, map). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
CHAT-02 | AI Chat Assistant | Chat assistant responds to a basic safety question | 1. Open the chat widget. 2. Ask a simple question, e.g. 'Is Alexanderplatz safe at night?' | Chat widget is loaded | Message: 'Is Alexanderplatz safe at night?' | Assistant returns a relevant, readable response within a reasonable wait time (with a loading indicator while waiting). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a few suggested starter questions under the chat input would help first-time users.
CHAT-03 | AI Chat Assistant | Chat widget can be minimised/closed and reopened | 1. Open the chat widget. 2. Close/minimise it. 3. Reopen it. | Chat widget is loaded | N/A | Widget closes and reopens smoothly without losing the page state or breaking the layout. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-01 | General UX | Navigation drawer / menu is accessible from any page | 1. From Home, open the navigation drawer. 2. Navigate to each listed page (Home, Incident, Profile, etc.). | App loaded | N/A | Nav drawer opens consistently and every menu item routes to the correct page without a blank/broken screen. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-02 | General UX | Error dialog appears for a failed network request | 1. Disconnect from the internet (or simulate a slow/failed connection). 2. Attempt a route search. | Network is disabled or throttled | N/A | A clear, non-technical error dialog is shown to the user (not a blank page or console-only error). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-03 | General UX | App is usable on a mobile phone screen (responsive layout) | 1. Open the app on a mobile phone (or emulate ~375px width). 2. Perform a route search and view a route's details. | N/A | Same route search as HOME-01 | Layout adapts cleanly: no overlapping text/buttons, all key actions remain reachable and tappable with one thumb. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: slightly larger tap target on the travel-mode toggle would help one-thumb use.
UX-04 | General UX | App is usable on a tablet screen | 1. Open the app on a tablet (or emulate ~768-1024px width). 2. Navigate through Home, Route Details, and Incident Report. | N/A | N/A | Layout uses the extra space sensibly (no huge empty gaps or cramped text) and remains fully functional. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-05 | General UX | Text and buttons are legible and touch-friendly on mobile | 1. On a mobile device, review font sizes and button sizes across Home, Login, and Incident Report pages. | Testing on mobile device | N/A | Text is readable without zooming; buttons/links are large enough to tap accurately (no accidental mis-taps). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-06 | General UX | Logout works and protects logged-in-only pages afterwards | 1. Log in. 2. Log out via profile/nav. 3. Attempt to directly open Route Details or Profile URL again. | Logged in | N/A | User is logged out cleanly, and attempting to access member-only pages afterwards redirects to Login instead of showing data. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a brief 'You have been logged out' toast would make the action feel more confirmed.
UX-07 | General UX | Page load performance feels acceptable to the user | 1. Open https://safepath.duckdns.org/home on a normal home/mobile connection. 2. Time how long until the page is interactive. | N/A | N/A | Home page becomes usable (map + search form ready) within a few seconds; a loading indicator is shown if it takes longer. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-08 | General UX | Browser back/forward buttons behave predictably | 1. Navigate Home → search → Route Details → use browser Back button. 2. Use browser Forward button. | N/A | N/A | Back/Forward move between the expected pages/states without breaking the app or losing critical context. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-09 | General UX | Consistent branding and terminology across pages | 1. Browse through Home, Login, Register, Incident Report, and Profile pages. 2. Compare wording, icons, and colour scheme. | N/A | N/A | 'SafePath Berlin' branding, colour palette, and terminology (e.g. 'Safe Route') are consistent across all pages. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
UX-10 | General UX | Cross-browser check on a second major browser | 1. Repeat HOME-01 and LOGIN-01 on a second browser (e.g. Firefox if primary testing was on Chrome). | N/A | N/A | Core flows (search, login) work the same way with no layout breakage on the second browser. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.

## Admin UAT Test Cases
Test ID | Module | Test Scenario | Test Steps | Preconditions | Test Data | Expected Result | Test Device / Browser | Actual Result | Status | Priority | Tester | Test Date | Remarks
ADM-01 | Admin Access | Non-admin user cannot open the Admin Dashboard | 1. Log in with a regular (non-admin) account. 2. Manually browse to /overview. | Logged in as a standard user (role: Member) | Standard user account | User is redirected away (e.g. to Home) and never sees Admin Dashboard content; no data leaks in the process. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: log the blocked access attempt itself as a security event for admins to review later.
ADM-02 | Admin Access | Admin user can access the Admin Dashboard from the nav menu | 1. Log in with an admin account. 2. Open the nav drawer. 3. Click 'Dashboard'. | Logged in as Admin | Admin test account | 'Dashboard' item is visible in the nav and opens the Admin Dashboard with all 5 tabs (Overview, Search Logs, Incident Logs, User Management, Login Logs). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a pinned shortcut or keyboard shortcut straight to Dashboard would save a few clicks.
ADM-03 | Admin Access | Guest (not logged in) is redirected when opening /overview directly | 1. Without logging in, browse directly to https://safepath.duckdns.org/overview. | Not logged in | N/A | User is redirected to Login instead of any admin content being shown. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-04 | Admin Access | Switching between dashboard tabs is smooth and preserves each tab's state | 1. Log in as Admin. 2. Open each tab in turn: Overview, Search Logs, Incident Logs, User Management, Login Logs. 3. Return to a previously visited tab. | Logged in as Admin, on Dashboard | N/A | Each tab loads its own content correctly; returning to a tab does not require a full page reload or lose filters entered earlier. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: show a small 'last refreshed' timestamp on each tab so admins know how fresh the data is.
ADM-05 | Admin - Overview | Overview stat cards show accurate summary numbers | 1. Go to Dashboard > Overview tab. 2. Review the stat cards (e.g. totals with trend chips) at the top. | Logged in as Admin | N/A | Stat cards load without errors and values look consistent with what's in Search Logs / Incident Logs (spot-check one). | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: let admins pick the stat-card date range (7/30/90 days) instead of a fixed window.
ADM-06 | Admin - Overview | 'Most Searched Places' list reflects real search activity | 1. As a regular user, search for the same destination 3 times. 2. Log in as Admin and check Overview > Most Searched Places. | Logged in as Admin; some searches exist | Repeat search e.g. 'Brandenburg Gate' x3 | The searched place appears in the list with an updated count and proportional progress bar. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: clicking a place in the list could pre-fill it into a new search for a quick spot-check.
ADM-07 | Admin - Overview | 'Most Incident Report Places' filters correctly by incident type | 1. Go to Overview tab. 2. In 'Most Incident Report Places', click one or more incident type chips (e.g. 'Poor lighting'). 3. Observe the list update. | Logged in as Admin; incident reports exist | Select 1-2 incident type filters | List updates to only reflect reports matching the selected type(s); 'Most common' label hides correctly when only one type is selected. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a 'select all types' toggle above the incident-type chips would reset filters faster.
ADM-08 | Admin - Overview | Overview handles the empty-data state gracefully | 1. View Overview tab on a fresh environment/test account with no search or incident history. | No search/incident data exists yet | N/A | Friendly empty-state messages ('No route searches yet.' / 'No incident reports yet.') are shown instead of blank cards or errors. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-09 | Admin - Search Logs | Search logs table lists route searches with safety score and status | 1. Go to Dashboard > Search Logs tab. 2. Review the table rows. | Logged in as Admin; search history exists | N/A | Table shows user (name/email or 'Guest'), safety score chip (colour-coded by risk level), and status chip per row. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: allow sorting the table by safety score to spot risky searches more quickly.
ADM-10 | Admin - Search Logs | Filter search logs by keyword | 1. On Search Logs tab, type a keyword (e.g. a place name or user email) into 'Filter search logs'. | Logged in as Admin; search history exists | Keyword: a known place name | Table updates live to show only matching rows; clearing the filter restores the full list. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: remember the last-used filter keyword when the admin returns to this tab.
ADM-11 | Admin - Search Logs | Refresh button reloads latest search logs | 1. On Search Logs tab, perform a new route search in another session/tab as a regular user. 2. Back in Admin, click the refresh icon. | Logged in as Admin | N/A | A loading state briefly shows, then the new search log entry appears without a full page reload. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: show a small spinner directly on the refresh icon while reloading.
ADM-12 | Admin - Search Logs | Guest searches are labelled clearly and don't expose a fake identity | 1. As a guest, perform a route search without logging in. 2. In Admin > Search Logs, find that row. | A guest (non-logged-in) search was just performed | N/A | Row shows 'Guest' rather than a blank, broken, or misleading user name/email. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-13 | Admin - Incident Logs | Incident logs table lists all submitted reports with type chips | 1. Go to Dashboard > Incident Logs tab. 2. Review the table. | Logged in as Admin; incident reports exist | N/A | Each row shows a colour-coded incident type chip; table loads without errors. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: light row colour-coding by incident type would make the list easier to scan.
ADM-14 | Admin - Incident Logs | View incident detail via the eye icon | 1. On Incident Logs tab, click the eye/view icon on a report row. | Logged in as Admin; at least one incident exists | N/A | A modal opens showing full report detail (type, location, date/time, details, reporter) that matches what was submitted. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: 'previous / next report' buttons inside the modal would help review reports without closing each time.
ADM-15 | Admin - Incident Logs | Close button on incident detail modal works | 1. Open an incident detail modal. 2. Click the close (X) icon. | Incident detail modal is open | N/A | Modal closes cleanly and returns to the Incident Logs table without page reload. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-16 | Admin - Incident Logs | Filter incident logs by keyword | 1. On Incident Logs tab, type a keyword (e.g. location name) into 'Filter incident logs'. | Logged in as Admin; incident reports exist | Keyword: a known location | Table filters live to matching rows only; clearing the filter restores full list. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: allow filtering by date range in addition to keyword.
ADM-17 | Admin - User Management | User list loads with pagination (server-side) | 1. Go to Dashboard > User Management tab. 2. Scroll/paginate through the user table. | Logged in as Admin; more than one page of users exists | N/A | Users load per page correctly, matching the total user count shown, with no duplicate or missing rows across pages. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: let the admin choose rows-per-page (10/25/50) instead of a fixed page size.
ADM-18 | Admin - User Management | Search users by name or email | 1. On User Management tab, type into 'Search by name or email'. | Logged in as Admin; multiple users exist | A known user's name or partial email | Table filters to matching users only; search is case-insensitive and works for partial matches. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: search-as-you-type felt slightly slow on a large user list; a short debounce delay would feel smoother.
ADM-19 | Admin - User Management | Add a new user via the 'Add User' dialog | 1. Click the add-user button. 2. Fill Name, Email, and Role. 3. Click 'Save User'. | Logged in as Admin | Name: QA Test User, Email: qatest@safepath.com, Role: Member | New user is created, a success confirmation (snackbar) appears, and the user shows up in the table without a manual refresh. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: auto-suggest a temporary password so admins do not have to think one up.
ADM-20 | Admin - User Management | Edit an existing user's role | 1. Click the edit (pencil) icon on a user row. 2. Change Role from 'Member' to 'Admin'. 3. Click 'Save User'. | Logged in as Admin; a non-admin test user exists | Role change: Member → Admin | Change is saved, table reflects the new role immediately, and a confirmation is shown. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: show a short confirmation summary (e.g. 'Role changed from Member to Admin') in the success message.
ADM-21 | Admin - User Management | Delete a user requires confirmation | 1. Click the delete (trash) icon on a user row. 2. Review the confirmation dialog. 3. Click 'Cancel' first, then repeat and click confirm delete. | Logged in as Admin; a disposable test user exists | A test user created for this scenario | Cancel aborts safely with no change; confirming removes the user from the table and shows a success snackbar. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: show the user's name inside the delete-confirmation dialog to avoid removing the wrong row by mistake.
ADM-22 | Admin - User Management | Admin cannot accidentally lock themselves out (self role-change safeguard) | 1. Log in as the only Admin account. 2. Try to edit your own user and change Role from Admin to Member, or delete your own account. | Logged in as the sole Admin | Self account | App either blocks this action with a warning, or clearly confirms the consequence before allowing it, avoiding an accidental total lockout. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a clearer warning banner (not only a dialog) when editing your own account would add extra safety.
ADM-23 | Admin - User Management | Save User validates required fields | 1. Click 'Add User'. 2. Leave Name or Email blank. 3. Click 'Save User'. | Logged in as Admin | Email left blank | Form blocks submission and indicates the missing required field(s) rather than saving an incomplete user. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-24 | Admin - Login Logs | Login logs list shows success and failed attempts with clear status | 1. Go to Dashboard > Login Logs tab. 2. Review table rows for both successful and failed attempts. | Logged in as Admin; login history includes at least one failed attempt | N/A | Successful logins show a green 'Success' style chip; failed attempts show a red/error chip, clearly distinguishable at a glance. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | High | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: a small map icon or tooltip showing the approximate location of a login attempt.
ADM-25 | Admin - Login Logs | Filter login events by keyword | 1. On Login Logs tab, type into 'Filter login events' (e.g. a user email). | Logged in as Admin; login history exists | A known user's email | Table filters live to matching rows; clearing the filter restores the full list. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a quick success/failed status toggle would help alongside the existing free-text search.
ADM-26 | Admin - Login Logs | Refresh reloads the latest login events | 1. In another session, log in/out as a test user to generate a new event. 2. Back in Admin > Login Logs, click refresh. | Logged in as Admin | N/A | New login event appears in the table after refresh without a full page reload. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Low | May Pyae Phyo Thaw | 2026-08-15 | Passed.
ADM-27 | Admin - General UX | Admin Dashboard is usable on a tablet screen | 1. Open Admin Dashboard on a tablet (or emulate ~768-1024px width). 2. Navigate through all 5 tabs and open a data table row action. | Logged in as Admin, tablet viewport | N/A | Tabs, tables, and dialogs remain usable — tables scroll horizontally if needed rather than breaking the layout. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Nice to have: sticky tab headers when scrolling long tables on tablet would help keep orientation.
ADM-28 | Admin - General UX | Loading and error states are clear across all admin tables | 1. Throttle/disable network. 2. Open each tab (Search Logs, Incident Logs, User Management, Login Logs) and observe loading/error handling. | Logged in as Admin, network throttled or disabled | N/A | Each table shows a loading indicator while fetching and a readable error alert if the fetch fails, never a silently blank table. | Desktop - Chrome Tablet - iPadOS Safar | Matches expected result. | Pass | Medium | May Pyae Phyo Thaw | 2026-08-15 | Passed. Convenience: a small 'reconnected' toast once the network returns would reassure admins during outages.

## Summary
SafePath Berlin – UAT Summary
Total Scenarios (User + Admin) | 73
Passed | 73
Failed | 0
Blocked | 0
Not Executed | 0
Pass Rate | 100%
By Module – User
Module | # Scenarios
Home / Route Search | 10
Route Details | 3
Login | 5
Register | 4
Incident Report | 7
Profile | 3
AI Chat Assistant | 3
General UX | 10
By Module – Admin
Module | # Scenarios
Admin Access | 4
Admin - Overview | 4
Admin - Search Logs | 4
Admin - Incident Logs | 4
Admin - User Management | 7
Admin - Login Logs | 3
Admin - General UX | 2